## Sheet1
S.NO.	ISSUE	CHECK ITEM	ISSUE TYPE	STATUS	DEVELOPER STATUS	QA REMARKS		Developer Comments
1	Login>>login box,when we	Login	Design	Open	Not a issue			Not able to reproduce
	click on login without any
	text on fields,then a design
	issue appears on box

2	Forgot password not	forgot password	functionality	Open	Pending			Not Implemented yet.
	working

3	While registering a text called	request account	design issue	Open	Fixed			Done
	Address1 is there but there
	is no space between address
	And 1

4	login>>request account >>	request account	design issue	Open	Not a issue			Not able to reproduce
	check validations of all the field
	then click on dropdown of the
	field state

5	Character limit is not set	request account	functionality	Open
	in the request account modules

6	Validation issue in
	password and confirm	request account	functionality	Open
	Password , when we write
	password , then click on
	confirm password it automatically
	gives the validation

7	Filling all the fields and click on	request account	functionality	Open
	register an error occurs

8	login(submitter)>>edit project>>	edit project	design issue	Open
	add attachment and then add
	a long comment a design issue
	will appear

9	while deleting any project it should	Project	functionality	Open
	ask once that are you sure wanna
	delete it

10	Login>>user request dashboard,	user request	Design	Open
	in fields there can be sorting arrows	dashboard

11	login>>Edit request>>viewing the	edit request	Design	Open
	attachement but unable to see

12	Login>>new request >>zip code no	new request	functionality	Open
	character limit is set

13